INTERNAL RUN-OF-SHOW BUCA vs. Bluebonnets · April 23, 2026 · GWEN ONLY — COMMAND DOC

⚠ This is your day-of command document. Print it. Have it on you at all times. Everything else is secondary.

PRE-EVENT CHECKLIST — APRIL 22 NIGHT

- Event bag packed: name badges, sign-in sheets, printed ROS (x3), speaker name cards, notebooks, pens, feedback forms

- Thomas briefed — 30 min check-in call done

- Statler room confirmed with Dee — setup, F&B, A/V

- All 9 speakers confirmed attending — zero question marks

- Happy hour sponsor confirmed (Dante or Jarred — clarify who)

- Registration link live and tested

- Final headcount sent to Dee for F&B guarantee

MORNING SEQUENCE — APRIL 23

| TIME | ACTION | STATUS |
| --- | --- | --- |
| 7:30 AM | Arrive at Statler. Walk the room. Check signage, table setup, materials placement. | [ ] |
| 7:45 AM | Check in with Dee — confirm F&B timing and A/V setup. | [ ] |
| 8:00 AM | A/V walkthrough with venue tech. Test all presenter connections. | [ ] |
| 8:30 AM | Place name badges, notebooks, pens, and feedback forms at each seat. | [ ] |
| 9:00 AM | F&B confirmed and in position. | [ ] |
| 9:15 AM | Speaker check-in opens. Greet each speaker. Confirm they have what they need. | [ ] |
| 9:30 AM | All speakers present. Thomas accounted for. | [ ] |
| 9:45 AM | Sound check with all mics. Confirm AV is loaded. | [ ] |
| 9:55 AM | Take position at registration table. | [ ] |
| 10:00 AM | Doors open. Welcome attendees. Direct to sign-in. | [ ] |
| 10:10 AM | Signal Thomas — 2 minutes to open. | [ ] |

TIME SIGNALS FOR SPEAKERS

Use these signals consistently so speakers know without disruption:

| SIGNAL | MEANING |
| --- | --- |
| 5 fingers held up | 5 minutes remaining |
| 2 fingers | 2 minutes remaining |
| 1 finger + eye contact | Wrap now — 30 seconds |
| Throat cut gesture | Stop — over time, hand to Thomas |

EMERGENCY PROTOCOLS

- Speaker no-show: notify Thomas immediately. Have a 15-min filler ready (extended Q&A or open discussion prompt).

- A/V failure: Dee Skinner 469-776-3722. Speakers present verbally while tech is resolved.

- Room runs hot (over capacity): alert Dee. Do not turn people away without checking with Thomas.

- Thomas runs long: step to the front of the room, hold up 2 fingers. He knows the signal.

- Attendee complaint or issue: handle quietly off to the side. Never in front of the room.

KEY CONTACTS

| Thomas Wagner | 512-409-0352 |
| --- | --- |
| Dee Skinner (Statler) | 469-776-3722 |
| AV Contact | [CONFIRM WITH DEE] |
| Catering Contact | [CONFIRM WITH DEE] |