## Dashboard
ZENITH RISK STRATEGIES
2026 COST CONTAINMENT SUMMIT SERIES · MASTER CONFERENCE PLANNER & TRACKER
Order Before Growth · Discipline Before Scale
Last updated: April 28, 2026
SERIES AT A GLANCE
# | City | Date | Theme | Venue | Status
1 | Dallas, TX | April 23, 2026 | BUCA vs. Bluebonnets | The Statler Dallas | ✓ COMPLETE
2 | Hilton Head, SC | May 29, 2026 | Logic in the Lowcountry | Palmetto Dunes Oceanfront | One Month Away
3 | Chicago, IL | June 18, 2026 | Engineered to Win | TBD — RFP in market | RFP distributed
4 | Denver, CO | July 23, 2026 | TBD | TBD | Planning
HOW TO USE THIS WORKBOOK
· One tab per conference: Dallas · Hilton Head · Chicago · Denver (in series order).
· Each conference tab contains: at-a-glance facts, speaker roster, attendee list (where applicable), venue & vendor contacts, sponsorship structure, budget snapshot, master task plan, run-of-show, and open items.
· Tasks are grouped by Phase (Foundation → Build → Final Prep → Day-Of → Post-Event) and ordered by date within each phase.
· Every task carries a Category tag: Speaker Coordination · Venue & Logistics · Sponsorship · Marketing & Outreach · Registration · Budget & Contracts · Travel · Day-Of · Post-Event.
· Status, Owner, Priority, and Category use dropdowns. Status auto-colors as you update.
· Series Dashboard tab shows cross-event critical open items + status by city. Updates recorded with date and highlight.
STATUS LEGEND
Complete | Task finished. No further action.
In Progress | Active work. Track to deadline.
Blocked | Cannot move — escalate.
Not Started | Future task. No action yet.
N/A | Not applicable to this event.
PHASE FRAMEWORK
Phase 1 — Foundation | T-30 to T-90 days. Venue contract, speakers, registration, hotel block.
Phase 2 — Build | T-15 to T-30 days. One-pagers, social spotlights, Apollo + LinkedIn outreach, speaker briefs.
Phase 3 — Final Prep | T-1 to T-14 days. Print, headcount, day-of details, AV walkthrough, Thomas briefing, event bag.
Phase 4 — Day-Of | Event day. Setup, registration, ROS execution, reception, close.
Phase 5 — Post-Event | T+1 to T+10 days. Thank-yous, recap, invoices, internal debrief, kick next event.
OWNERS
Gwen Diede | Events & Marketing Manager | gdiede@zenithriskstrategies.com | 512-787-7922
David Reinhold | Director of Operations | dreinhold@zenithriskstrategies.com
Thomas Wagner | CEO & Founder | twagner@zenithriskstrategies.com

## Dallas
DALLAS · BUCA vs. BLUEBONNETS — COMPLETE
Thursday · April 23, 2026 · The Statler Dallas · Event 1 of 4 · Series Anchor
AT A GLANCE
Status | ✓ COMPLETE — held April 23, 2026
Event | BUCA vs. Bluebonnets
Date | April 23, 2026
Venue | The Statler Dallas · Junior Ballroom · 1914 Commerce St, Dallas TX 75201
Schedule held | 11:00 AM – 4:00 PM (working summit) + Happy Hour
Final registered | 35 (9 speakers + 26 attendees)
Series role | Event 1 of 4 — Anchor / Thesis-Setting
Now in | Phase 5 — Post-Event execution (week of Apr 27)
SPEAKER ROSTER
Speaker | Title / Company | Topic | Bio | Headshot | Slide Deck | Spotlight | Hotel | Notes
Thomas Wagner | CEO, Zenith Risk Strategies | Welcome · Captives · Close | Yes | Yes | Delivered | Posted | Self | Anchored thesis. Opened + closed.
Jarred Pierce | Founder/CEO, Unity Preferred Network | Network Access & PPO | Yes | Yes | Delivered | Posted | 4/22–4/24 | Co-sponsor.
Ashley Jones, PharmD | Veracity Benefits | Pharmacy & Benefits Navigation | Yes | Yes | Delivered | Posted | 4/22 | Co-presented w/ Tim.
Tim Hyde | VP Strategic Partnerships, Veracity Benefits | Pharmacy & Benefits Navigation | Yes | Yes | Delivered | Posted | 4/22 | Co-presented w/ Ashley.
David Balat | CEO, Direct Care Alliance | Direct Care / Policy Frame | Yes | Yes | Delivered | Posted | 4/23 | Held the room on policy frame.
Dante Panella | Co-Founder, PriceMDs | Bundled Pricing & Specialty | Yes | Yes | Delivered | Posted | 4/22–4/23 | Sole Happy Hour sponsor.
Courtney DeWitt | Director of Sales, Kerix Health | Direct Primary Care | Yes | Yes | Delivered | Posted | 4/22 | Kerix lead on stage.
David Bryan Reinhold | Zenith Risk Strategies | Zenith Strategy / Co-Host | Yes | Yes | Delivered | Posted | Self | Zenith on-stage co-presence.
Brett Morris | Founder/CEO, Samaritan Fund Program | Claim Strategy | Yes | Yes | Delivered | Posted | Virtual | Virtual presenter — confirmed in-person for Hilton Head.
ATTENDEE ROSTER (FINAL)
# | Name | Company
1 | Mark Abare | Freshbenies
2 | Tracy Berwick | Precision Health TPA
3 | Bud Brooks | Luminary Health
4 | Javier Castaneda | Christensen Group
5 | Nancy Childs | Simpatico Benefits
6 | Warren Cleveland | Captive Coalition
7 | Jef Drummond | Ensure Benefits
8 | Stephanie Forand | ISS World
9 | Ryan Fridborg | IMA Corp
10 | Rick Grizzle | Physicians Collaborative Health
11 | Craig Herndon | EmpirX Health
12 | Robb Higdon | Fair Market Health
13 | Michael Hurley | Champion Insurance
14 | Tommy Lavelle | Holmes Murphy
15 | Chris Leverett | TexCap Insurance
16 | Jonathan Lopez | —
17 | Robbie McCullough | Epic Brokers
18 | Chris Orta | Champion Insurance
19 | Brian Payson | Baldwin Risk Partners
20 | Theresa Simonsen | TrueScripts
21 | Larry Thexton | Bravo Health Partners
22 | Jake Tsika | Hilb Group
23 | Dawn Walker | Precision Health TPA
24 | Will Warren | —
25 | Rex Wilcox | TrueScripts
26 | Tim Woodyard | Bravo Health Partners
VENUE & VENDOR CONTACTS
Item | Detail | Status
Venue | The Statler Dallas (Curio Collection by Hilton) | Held
Address | 1914 Commerce St, Dallas TX 75201
Room used | Junior Ballroom | Held
Catering Sales Manager | Anastasia Elie · anastasia.elie@hilton.com · 972-776-3762 | Wrap-up phase
AV Provider | Encore Global — Fermin Martinez | Held
Final invoice / billing | Pending reconciliation with Anastasia | Open
SPONSORSHIP STRUCTURE
Slot | Sponsor / Companies | Status
Happy Hour Sponsor (sole) | Dante Panella · PriceMDs | Delivered
Conference Co-Sponsors | Zenith, Unity, Veracity, Kerix, PriceMDs, Direct Care Alliance, Samaritan | Delivered
Cost-share invoices | To be issued by April 30 | Open
BUDGET SNAPSHOT
Line Item | Amount | Status
Room Rental — Junior Ballroom | $500 | Final
F&B (incl. svc + tax) | ≈ $6,900 | Pending invoice
AV Package | $700 | Final
Marketing / Print / Notebooks | Tracking | Closing out
Total — Pre-reconciliation | ≈ $8,100 | Pending final
Cost-share split | 7-way · est. $1,150/co. | To finalize w/ invoices
MASTER TASK PLAN — BY PHASE → DATE
Phase | Category | Due Date | Task | Owner | Priority | Status
Phase 1 — Foundation
Phase 1 — Foundation | Speaker Coordination | Mar 20 | Post-call recap email to all speakers + deck | Gwen | P2 — High | Complete
Phase 1 — Foundation | Marketing & Outreach | Mar 20 | Registration link to Thomas + Jarred for LinkedIn | Gwen | P2 — High | Complete
Phase 1 — Foundation | Marketing & Outreach | Mar 23 | Initial broker outreach (Sequence 3A) | Gwen | P2 — High | Complete
Phase 1 — Foundation | Travel | Mar 24 | Statler room block — booking links sent to speakers | Gwen | P2 — High | Complete
Phase 1 — Foundation | Speaker Coordination | Mar 31 | All bios + headshots received | Gwen | P2 — High | Complete
Phase 2 — Build
Phase 2 — Build | Marketing & Outreach | Apr 1 | Apollo.io 454-contact DFW outreach activated | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | Apr 1 | 29-day LinkedIn campaign launched | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | Apr 3 | Marketing one-pager built + distributed | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | Apr 3 | Speaker spotlight social campaign launched | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | Apr 5 | Sequence 3B sent to non-responders | Gwen | P2 — High | Complete
Phase 2 — Build | Speaker Coordination | Apr 10 | Speaker Brief + ROS distributed | Gwen | P2 — High | Complete
Phase 2 — Build | Speaker Coordination | Apr 10 | Slide decks received | Speaker | P2 — High | Complete
Phase 2 — Build | Venue & Logistics | Apr 10 | Statler walk — room, F&B, AV | Joint | P2 — High | Complete
Phase 3 — Final Prep
Phase 3 — Final Prep | Marketing & Outreach | Apr 14 | Last-call attendee outreach (3C) | Gwen | P2 — High | Complete
Phase 3 — Final Prep | Day-Of | Apr 15 | Print ROS, name cards, signage, notebooks | Gwen | P2 — High | Complete
Phase 3 — Final Prep | Venue & Logistics | Apr 16 | Final headcount to Statler (F&B guarantee) | Joint | P2 — High | Complete
Phase 3 — Final Prep | Speaker Coordination | Apr 18 | Final confirmation + day-of details to speakers | Gwen | P2 — High | Complete
Phase 3 — Final Prep | Day-Of | Apr 18 | Final ROS locked + distributed | Gwen | P2 — High | Complete
Phase 3 — Final Prep | Registration | Apr 22 | Day-before reminder to attendees | Gwen | P2 — High | Complete
Phase 3 — Final Prep | Speaker Coordination | Apr 22 | Thomas briefing | Joint | P2 — High | Complete
Phase 3 — Final Prep | Day-Of | Apr 22 | Pack event bag — badges, ROS, notebooks | Gwen | P2 — High | Complete
Phase 4 — Day-Of
Phase 4 — Day-Of | Day-Of | Apr 23 · 8:00 AM | Arrive Statler · room walk · materials | Gwen | P2 — High | Complete
Phase 4 — Day-Of | Venue & Logistics | Apr 23 · 9:00 AM | AV walkthrough + speaker check-in | Gwen | P2 — High | Complete
Phase 4 — Day-Of | Registration | Apr 23 · 11:00 AM | Doors open · sign-in | Gwen | P2 — High | Complete
Phase 4 — Day-Of | Day-Of | Apr 23 · 11AM–4PM | Run summit per ROS | Joint | P2 — High | Complete
Phase 4 — Day-Of | Sponsorship | Apr 23 · 4:00 PM | Happy Hour — PriceMDs sponsor execution | Gwen | P2 — High | Complete
Phase 4 — Day-Of | Day-Of | Apr 23 · Close | Collect feedback forms | Gwen | P2 — High | Complete
Phase 5 — Post-Event
Phase 5 — Post-Event | Post-Event | 2026-04-28 | Email 4A — Attendee thank-you + Hilton Head invite | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Post-Event | 2026-04-28 | Email 4B — Speaker thank-you + Hilton Head ask | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Post-Event | 2026-04-28 | Email 4C — No-show follow-up | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Speaker Coordination | Apr 28 | Distribute Speaker Recap Packet | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Marketing & Outreach | Apr 30 | LinkedIn recap post — Hilton Head CTA | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Post-Event | Apr 30 | Internal recap doc — wins / gaps / learnings | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Budget & Contracts | Apr 30 | Issue cost-share invoices (6 companies) | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | May 1 | Photo gallery distribution | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Budget & Contracts | May 5 | Reconcile Statler invoice w/ Anastasia | Gwen | P2 — High | Complete
Phase 5 — Post-Event | Speaker Coordination | May 7 | Speaker honorariums processed (10 biz days) | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Speaker Coordination | May 9 | Hilton Head speaker confirmations deadline | Speaker | P2 — High | In Progress
RUN OF SHOW
Time | Action | Owner
8:00 AM | Arrive Statler — room walk, signage, materials | Gwen
9:00 AM | AV walkthrough w/ Fermin / Encore | Gwen + AV
10:30 AM | Speaker check-in + sound check | Gwen
11:00 AM | Doors open / Welcome — Thomas Wagner | Thomas
11:30 AM | Brett Morris — Employer Funding Strategy (virtual) | Brett
12:00 PM | Lunch + networking | All
12:30 PM | Courtney DeWitt — DPC | Courtney
1:00 PM | Ashley Jones + Tim Hyde — Pharmacy & Benefits Nav | Ashley/Tim
2:00 PM | Dante Panella — Bundled Pricing & Specialty | Dante
2:30 PM | David Balat — Direct Care Alliance | David
3:00 PM | Jarred Pierce — Network Access & PPO | Jarred
3:30 PM | Broker Hot Seat — Panel Town Hall | All Speakers
4:00 PM | Thomas — Closing Remarks | Thomas
4:00 PM | Happy Hour & Networking — sponsored by PriceMDs | Dante
OPEN ITEMS / RISKS
Item | Owner | Due | Priority
Reconcile final Statler invoice w/ Anastasia | Gwen | May 5 | P2 — High
Issue cost-share invoices to 6 sponsoring companies | Gwen | Apr 30 | P1 — Critical
Process speaker honorariums (10 business days) | Gwen | May 7 | P2 — High
Photo gallery — confirm photographer turnaround + send links | Gwen | May 1 | P2 — High
Update speaker tracker w/ Hilton Head confirmations as they come in | Gwen | Rolling | P2 — High

## Hilton Head
HILTON HEAD · LOGIC IN THE LOWCOUNTRY
Friday · May 29, 2026 · Palmetto Dunes Oceanfront Resort · Event 2 of 4 · 32 days out
AT A GLANCE
Event | Logic in the Lowcountry
Tagline | Clarity in Complex Terrain · Structure where Others See Swamp
Date | Friday, May 29, 2026
Venue | Palmetto Dunes Oceanfront Resort · Hilton Head Island, SC
Schedule | 11:00 AM – 4:30 PM (working summit) + Happy Hour & Networking
Audience target | 35–50 brokers, TPAs, CFOs, HR leaders (Southeast)
Series role | Event 2 of 4 — Execution & Stewardship
Status | Venue confirmed · Agenda locked · Speakers verbal/contract pending · 32 days out
SPEAKER ROSTER
Speaker | Title / Company | Topic | Bio | Headshot | Slide Deck | Spotlight | Hotel | Notes
Thomas Wagner | CEO, Zenith Risk Strategies | Welcome & Cost Containment + Closing | Carryover | Yes | Pending | Pending | Self | Anchors. Opens 11:00, closes 4:00.
Brett Morris | CEO, Samaritan Fund Program | Employer Funding Strategy | Carryover | Yes | Pending | Pending | TBD | 11:30 slot. In-person this time.
Courtney DeWitt | Kerix Health | Direct Primary Care Navigation | Carryover | Yes | Pending | Pending | TBD | 12:30 slot.
Ashley Jones, PharmD | Veracity Benefits | Pharmacy & Benefits Navigation | Carryover | Yes | Pending | Pending | TBD | 1:00 slot. Co-presents w/ Tim.
Tim Hyde | Veracity Benefits | Pharmacy & Benefits Navigation | Carryover | Yes | Pending | Pending | TBD | 1:00 slot. Co-presents w/ Ashley.
Dante Panella | PriceMDs | Bundled Pricing & Specialty Strategy | Carryover | Yes | Pending | Pending | TBD | 2:00 slot.
David Balat | CEO, Direct Care Alliance | Direct Care Alliance | Carryover | Yes | Pending | Pending | TBD | 2:30 slot.
Jarred Pierce | Unity Preferred Network | Network Access & PPO Strategy | Carryover | Yes | Pending | Pending | TBD | 3:00 slot.
VENUE & VENDOR CONTACTS
Item | Detail | Status
Venue | Palmetto Dunes Oceanfront Resort | Confirmed
Region | Hilton Head Island, SC
Catering portal | DunesCateringAndEvents.com · 844-253-9289 | Active
Primary Contact | Dom (Palmetto Dunes) | Active
Secondary Contacts | Kayla, Lisa (Palmetto Dunes) | Active
F&B menus | Beverages, Breaks, Brunch/Lunch — received | Reviewing
Room / Layout | Rounds of 6–8 required · oceanfront preferred | Pending confirmation
AV Plan | Minimal in-house — mirror Dallas approach | Pending confirmation
Hotel Block | TBD — secure by May 1 | Open
SPONSORSHIP STRUCTURE
Slot | Sponsor / Companies | Status
Happy Hour Sponsor | TBD — Dante carryover candidate | Open
Conference Co-Sponsors | All speakers via cost-share (mirror Dallas) | Pending contracts
Cost-share structure | Equal split among co-sponsoring companies | Defined
BUDGET SNAPSHOT
Line Item | Amount | Status
Venue / Room | TBD — Palmetto Dunes quote pending | Pending
F&B Minimum | TBD — pending menu selections | Pending
AV | TBD — target minimal in-house | Pending
Hotel Block | TBD | Pending
Marketing / Print / Notebooks | TBD | Pending
Total Estimate | TBD post-final menu + AV | Pending
Cost-share Split | Equal among speaker companies | Mirror Dallas
MASTER TASK PLAN — BY PHASE → DATE
Phase | Category | Due Date | Task | Owner | Priority | Status
Phase 1 — Foundation
Phase 1 — Foundation | Speaker Coordination | 2026-04-28 | Hilton Head invite included in Email 4B speaker thank-you | Gwen | P2 — High | In Progress
Phase 1 — Foundation | Travel | Apr 28 | Initiate hotel block negotiation (Palmetto Dunes or partner) | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | Apr 28 | Confirm room layout (rounds of 6–8) + F&B menu selections | Gwen + Dom | P2 — High | Complete
Phase 1 — Foundation | Registration | Apr 30 | Set up Eventbrite listing (clone Dallas) | Gwen | P2 — High | Complete
Phase 1 — Foundation | Venue & Logistics | May 1 | Palmetto Dunes contract signed | Gwen | P2 — High | Complete
Phase 1 — Foundation | Sponsorship | May 1 | Issue speaker cost-share agreements (Lowcountry version) | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Marketing & Outreach | May 2 | LinkedIn Save-the-Date posts launched | Gwen | P2 — High | Complete
Phase 1 — Foundation | Marketing & Outreach | May 4 | Apollo.io Southeast broker list built | Gwen | P2 — High | Complete
Phase 1 — Foundation | Sponsorship | May 8 | Happy Hour sponsor confirmed | Joint | P2 — High | Complete
Phase 1 — Foundation | Speaker Coordination | May 9 | Speaker availability confirmed (response deadline) | Speaker | P2 — High | In Progress
Phase 2 — Build
Phase 2 — Build | Marketing & Outreach | May 8 | Lowcountry marketing one-pager finalized | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | May 11 | Logic in the Lowcountry flyer — print + digital | Gwen | P2 — High | Complete
Phase 2 — Build | Marketing & Outreach | May 11 | Speaker spotlight social rotation launched | Gwen | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | May 12 | Apollo broker outreach (Sequence 3A) | Gwen | P2 — High | Complete
Phase 2 — Build | Speaker Coordination | May 13 | Speaker call #2 — agenda + topic alignment | Joint | P2 — High | In Progress
Phase 2 — Build | Marketing & Outreach | May 15 | LinkedIn DM campaign — brokers/CFO segments | Gwen | P2 — High | In Progress
Phase 2 — Build | Speaker Coordination | May 18 | Slide decks due | Speaker | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | May 18 | Speaker Brief + ROS distributed | Gwen | P2 — High | Not Started
Phase 2 — Build | Venue & Logistics | May 19 | Venue walkthrough — room, F&B, AV | Gwen + Venue | P2 — High | Not Started
Phase 3 — Final Prep
Phase 3 — Final Prep | Marketing & Outreach | May 20 | Apollo follow-up sequence (3B) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | May 22 | Print ROS, name cards, signage, notebooks | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | May 22 | Final headcount to venue (F&B guarantee) | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Marketing & Outreach | May 25 | Last call attendee outreach (3C) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | May 25 | Final confirmation + day-of details to speakers | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | May 25 | Confirm AV needs from every speaker | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | May 26 | Final ROS locked + distributed | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Registration | May 27 | Day-before reminder to attendees | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | May 28 | Thomas briefing | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | May 28 | Pack event bag — badges, sign-in, ROS x3, notebooks | Gwen | P2 — High | Not Started
Phase 4 — Day-Of
Phase 4 — Day-Of | Day-Of | May 29 · AM | Arrive Palmetto Dunes — walk room, signage, materials | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Venue & Logistics | May 29 · AM | F&B + AV walkthrough | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Speaker Coordination | May 29 · 10:30 AM | Speaker check-in + sound check | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Registration | May 29 · 11:00 AM | Doors open — registration table | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | May 29 · 11AM–4PM | Run summit per ROS | Joint | P2 — High | Not Started
Phase 4 — Day-Of | Sponsorship | May 29 · 4:00 PM | Lowcountry Happy Hour execution | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | May 29 · 4:30 PM | Event close — collect feedback forms | Gwen | P2 — High | Not Started
Phase 5 — Post-Event
Phase 5 — Post-Event | Post-Event | May 30 | Email 4A — attendee thank-you + Chicago invite | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | May 30 | Email 4B — speaker thank-you + Chicago ask | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Marketing & Outreach | Jun 1 | LinkedIn recap post — Chicago CTA | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Jun 3 | Internal recap doc complete | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Budget & Contracts | Jun 5 | Cost-share invoices issued | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Speaker Coordination | Jun 5 | Chicago speaker outreach activation | Gwen | P2 — High | Not Started
RUN OF SHOW
Time | Action | Owner
8:30 – 9:15 AM | (Optional pre-event) Arrival prep — venue walk / AV / signage | Gwen
10:30 AM | Speaker check-in + sound check | Gwen
11:00 AM | Welcome & Cost Containment — Thomas Wagner | Thomas
11:30 AM | Employer Funding Strategy — Brett Morris | Brett
12:00 PM | Lunch & networking | All
12:30 PM | Direct Primary Care Navigation — Kerix Health (Courtney) | Courtney
1:00 PM | Pharmacy & Benefits Navigation — Veracity (Ashley + Tim) | Ashley/Tim
2:00 PM | Bundled Pricing & Specialty Strategy — Dante Panella | Dante
2:30 PM | Direct Care Alliance — David Balat | David
3:00 PM | Network Access & PPO Strategy — Jarred Pierce | Jarred
3:30 PM | Broker Hot Seat — Panel Town Hall | All Speakers
4:00 PM | Closing Remarks — Thomas Wagner | Thomas
4:00 PM | Lowcountry Happy Hour & Networking | All
4:30 PM | Event close | Gwen
OPEN ITEMS / RISKS
Item | Owner | Due | Priority
Lock Palmetto Dunes contract — room, F&B minimum, AV | Gwen + Dom | May 1 | P1 — Critical
Eventbrite listing live — clone Dallas structure | Gwen | May 1 | P1 — Critical
Speaker confirmations / Hilton Head cost-share agreements out | Gwen | May 9 | P1 — Critical
Hotel block secured | Gwen | May 1 | P1 — Critical
Happy Hour sponsor confirmed | Gwen + Thomas | May 8 | P2 — High
Apollo.io Southeast broker list built | Gwen | May 4 | P1 — Critical
LinkedIn Save-the-Date posts launched | Gwen | May 2 | P2 — High
Marketing one-pager (Lowcountry version) finalized | Gwen | May 8 | P2 — High
Logic in the Lowcountry flyer — printed + digital | Gwen | May 11 | P2 — High
Contingency: Speaker cancellation backup defined | Gwen + Thomas | May 15 | P2 — High
Contingency: AV-failure plan (journal-only facilitation) | Gwen | May 15 | P3 — Standard
Contingency: Weather plan (Hilton Head matters here) | Gwen + Venue | May 15 | P2 — High
Contingency: Low-attendance pivot (merge tables) | Gwen | May 15 | P3 — Standard

## Chicago
CHICAGO · ENGINEERED TO WIN
Thursday · June 18, 2026 · Venue TBD · Event 4 of 4 · Series Finale
AT A GLANCE
Event | Engineered to Win — Chicago Cost Containment Summit
Tagline | Most plans are assembled. Winning plans are engineered.
Date | Thursday, June 18, 2026
Venue | TBD — RFP in market (response deadline May 9)
Schedule | 8:30 AM Doors · 10:00 AM Summit · 4:15 PM Close · 4:30–6:30 PM Reception
Audience target | 50–75 brokers, TPAs, CFOs, HR leaders (Midwest corridor)
Series role | Event 4 of 4 — Series Finale
Speaker count | 5–6 featured speakers and panelists
Status | RFP distributed Apr 27 · Decision target May 15 · Contract May 16
SPEAKER ROSTER
Speaker | Title / Company | Topic | Bio | Headshot | Slide Deck | Spotlight | Hotel | Notes
Thomas Wagner | CEO, Zenith Risk Strategies | Welcome · Engineered to Win Framework · Captive Architecture · Close | Carryover | Yes | Pending | Not started | TBD | Anchors. Multiple slots.
TBD — Captive Architecture | Captive operator / actuary | The Chassis: Captive Structure as Load-Bearing Frame | Pending | Pending | Pending | Not started | TBD | 10:45 slot. Carryover candidate from Dallas/HH.
TBD — Networks | Network strategy lead | The Engine: Networks Engineered for Performance | Pending | Pending | Pending | Not started | TBD | 11:30 slot. Likely Jarred Pierce carryover.
TBD — Direct Care | DPC / bundled pricing | The Fuel System: Direct Care & Bundled Pricing | Pending | Pending | Pending | Not started | TBD | 1:15 slot. Likely Kerix or PriceMDs carryover.
TBD — Pharmacy | Pharmacy / PBM | The Pit Stop: Pharmacy Strategy Under Pressure | Pending | Pending | Pending | Not started | TBD | 2:00 slot. Likely Veracity carryover.
All Speakers | Panel | The Checkered Flag: Broker Hot Seat (moderated by Thomas) | — | — | — | — | — | 3:45 slot. Live, unscripted.
VENUE & VENDOR CONTACTS
Item | Detail | Status
Venue | TBD — RFP in market | Sourcing
RFP target venue types | Historic landmark, modern executive, design-forward boutique | Defined
Preferred candidates | Blackstone · Drake · LondonHouse · Sheraton Grand Riverwalk · Marriott Marquis · Hotel EMC2 | RFP'd
Reception requirement | Outdoor terrace / rooftop / river-view (priority, not preference) | Defined
Room layout | Rounds of 6–8 (no classroom, no theater) | Required
Service charge target | Below 24% at contract signing | Negotiation goal
AV | Large-format display · wireless mic · dedicated tech · high-speed WiFi | Defined
Decision date | May 15, 2026 (target) | Scheduled
Contract execution target | May 16, 2026 | Scheduled
SPONSORSHIP STRUCTURE
Slot | Sponsor / Companies | Status
Happy Hour / Reception Sponsor | TBD — finale-grade slot | Open
Conference Co-Sponsors | All speakers via cost-share (mirror Dallas) | Pending
Cost-share structure | Equal split among speaker companies | Defined
Series Finale positioning | Reserved for highest-tier sponsor opportunity | By design
BUDGET SNAPSHOT
Line Item | Amount | Status
Venue / Room | TBD — RFP responses by May 9 | Pending
F&B Minimum | TBD — Chicago-elevated menu (chef-driven) | Pending
AV | TBD — minimal but premium quality | Pending
Hotel Block | TBD — included in RFP | Pending
Marketing / Print / Notebooks | TBD — finale-grade collateral | Pending
Total Estimate | Higher than prior events — finale + Chicago premium | TBD
MASTER TASK PLAN — BY PHASE → DATE
Phase | Category | Due Date | Task | Owner | Priority | Status
Phase 1 — Foundation
Phase 1 — Foundation | Venue & Logistics | Apr 27 | RFP distributed to venue shortlist | Gwen | P2 — High | Complete
Phase 1 — Foundation | Speaker Coordination | Apr 28 | Thomas's Chicago invite list activation | Thomas + Gwen | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | May 9 | RFP response deadline — collect all proposals | Venue | P2 — High | Complete
Phase 1 — Foundation | Venue & Logistics | May 12 | Site virtual visit begin (3 days, May 12–14) | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | May 15 | Venue selection decision | Joint | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | May 16 | Venue contract executed | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Registration | May 18 | Eventbrite listing live | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Travel | May 18 | Hotel block secured | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Speaker Coordination | May 20 | Confirm Dallas/HH speaker carryovers + identify net-new Midwest speakers | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Sponsorship | May 22 | Speaker cost-share agreements issued | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Marketing & Outreach | May 22 | Build Midwest Apollo list (IL, WI, IN, MO) | Gwen | P2 — High | Not Started
Phase 2 — Build
Phase 2 — Build | Speaker Coordination | May 25 | Speaker bio + headshot deadline | Speaker | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | May 27 | Engineered to Win one-pager + flyer finalized | Gwen | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | May 27 | Speaker spotlight social rotation launched | Gwen | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | May 28 | Apollo broker outreach (Sequence 3A) — Midwest | Gwen | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | Jun 1 | Speaker call #2 — pillar alignment | Joint | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | Jun 3 | LinkedIn DM campaign — Midwest brokers/CFOs | Gwen | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | Jun 5 | Slide decks due | Speaker | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | Jun 5 | Speaker Brief + ROS distributed | Gwen | P2 — High | Not Started
Phase 3 — Final Prep
Phase 3 — Final Prep | Venue & Logistics | Jun 8 | Venue walkthrough | Gwen + Venue | P2 — High | Not Started
Phase 3 — Final Prep | Marketing & Outreach | Jun 10 | Apollo follow-up (3B) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jun 11 | Print ROS, name cards, signage, Field Journals | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | Jun 11 | Final headcount to venue (F&B guarantee) | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Marketing & Outreach | Jun 14 | Last-call attendee outreach (3C) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | Jun 14 | Final confirmation + day-of details to speakers | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | Jun 14 | Confirm AV needs from every speaker | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jun 15 | Final ROS locked + distributed | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Registration | Jun 17 | Day-before reminder to attendees | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | Jun 17 | Thomas briefing | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Sponsorship | Jun 17 | Confirm Reception sponsor logistics | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jun 17 | Pack event bag — badges, sign-in, ROS x3, journals | Gwen | P2 — High | Not Started
Phase 4 — Day-Of
Phase 4 — Day-Of | Day-Of | Jun 18 · 7:00 AM | Arrive venue — walk room, check signage + materials | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Venue & Logistics | Jun 18 · 7:30 AM | F&B + AV walkthrough | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Speaker Coordination | Jun 18 · 9:00 AM | Speaker check-in + sound check | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Registration | Jun 18 · 8:30 AM | Doors open — registration table | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | Jun 18 · 10AM–4:15PM | Run summit per ROS | Joint | P2 — High | Not Started
Phase 4 — Day-Of | Sponsorship | Jun 18 · 4:30 PM | Reception execution — Chicago skyline backdrop | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | Jun 18 · 6:30 PM | Event close — collect feedback forms | Gwen | P2 — High | Not Started
Phase 5 — Post-Event
Phase 5 — Post-Event | Post-Event | Jun 19 | Email 4A — attendee thank-you + Denver invite | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Jun 19 | Email 4B — speaker thank-you + Denver ask | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Marketing & Outreach | Jun 22 | LinkedIn recap post — Denver CTA | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Jun 25 | Internal recap doc complete | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Budget & Contracts | Jun 30 | Cost-share invoices issued | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Speaker Coordination | Jun 30 | Denver speaker outreach activation | Gwen | P2 — High | Not Started
RUN OF SHOW
Time | Action | Owner
8:30 AM | Doors open · Arrival & Registration · espresso bar + light breakfast | Gwen
10:00 AM | Welcome & Framing — Engineered to Win · Thomas Wagner | Thomas
10:20 AM | Working Session — Blueprint Gaps | Facilitator
10:45 AM | The Chassis: Captive Structure — TBD | Speaker TBD
11:30 AM | The Engine: Networks Engineered for Performance — TBD | Speaker TBD
12:15 PM | Plated Lunch · Broker-to-Broker Dialogue | All
1:15 PM | The Fuel System: Direct Care & Bundled Pricing — TBD | Speaker TBD
2:00 PM | The Pit Stop: Pharmacy Strategy Under Pressure — TBD | Speaker TBD
2:45 PM | Afternoon Break | All
3:00 PM | Captive Architecture: The Race-Ready Plan — Thomas Wagner | Thomas
3:45 PM | The Checkered Flag — Broker Hot Seat Panel | All Speakers
4:15 PM | Closing Reflection — Thomas Wagner | Thomas
4:30 PM | Networking Reception · Chicago skyline backdrop | All
6:30 PM | Event close | Gwen
OPEN ITEMS / RISKS
Item | Owner | Due | Priority
RFP distributed to venue shortlist | Gwen | Apr 27 | P1 — Critical
RFP responses received from all 6 venues | Gwen + Venues | May 9 | P1 — Critical
Site visits / walkthroughs of finalists | Gwen | May 12–14 | P1 — Critical
Venue selection decision | Gwen + Thomas | May 15 | P1 — Critical
Venue contract execution | Gwen | May 16 | P1 — Critical
Confirm Dallas/HH speaker carryovers for Chicago | Gwen | May 20 | P1 — Critical
Identify net-new Midwest speakers (if needed) | Gwen + Thomas | May 20 | P2 — High
Build Eventbrite listing | Gwen | May 18 | P1 — Critical
Issue speaker cost-share agreements | Gwen | May 22 | P1 — Critical
Hotel block secured | Gwen | May 18 | P1 — Critical
Build Midwest Apollo list (IL, WI, IN, MO) | Gwen | May 22 | P2 — High
Thomas's Chicago invite list activation (Wanza, BJ, Colton, Bryce, Drew, Vicki, Aaron Witner) | Thomas | Apr 28 | P1 — Critical

## Denver
DENVER · 2026 SUMMIT (PLANNING)
Thursday · July 23, 2026 · Venue TBD · Event 3 of 4
AT A GLANCE
Event | Denver Summit (working title TBD — "Engineered for Altitude" / "Reaching Benefits Heights")
Date | Thursday, July 23, 2026
Venue | TBD — sourcing begins post-Hilton Head
Schedule | TBD — model on Hilton Head structure (working summit)
Audience target | Brokers, TPAs, CFOs (Mountain West)
Series role | Event 3 of 4 — Mountain West Market
Status | Planning — date locked · venue + speakers TBD
SPEAKER ROSTER
Speaker | Title / Company | Topic | Bio | Headshot | Slide Deck | Spotlight | Hotel | Notes
Thomas Wagner | CEO, Zenith Risk Strategies | Welcome + Captive Architecture + Close | Carryover | Yes | Pending | Not started | TBD | Confirmed.
Carryover Speakers (TBD) | From Dallas / HH / Chicago | Pillar topics — to confirm post-Chicago | Pending | Pending | Pending | Not started | TBD | Confirm post-Chicago.
VENUE & VENDOR CONTACTS
Item | Detail | Status
Venue | TBD — Denver area | Sourcing
RFP target | Distribute by June 5, 2026 | Scheduled
Decision target | June 19, 2026 | Scheduled
Contract execution target | June 22, 2026 | Scheduled
AV / Layout | Mirror prior events — minimal in-house, rounds 6–8 | Defined
Hotel Block | TBD | Open
SPONSORSHIP STRUCTURE
Slot | Sponsor / Companies | Status
Happy Hour Sponsor | TBD | Open
Conference Co-Sponsors | All speakers via cost-share | Mirror Dallas
Cost-share structure | Equal split among speaker companies | Defined
BUDGET SNAPSHOT
Line Item | Amount | Status
Venue / Room | TBD | Pending
F&B Minimum | TBD | Pending
AV | TBD — minimal in-house preferred | Pending
Hotel Block | TBD | Pending
Marketing / Print | TBD | Pending
Total Estimate | TBD | Pending
MASTER TASK PLAN — BY PHASE → DATE
Phase | Category | Due Date | Task | Owner | Priority | Status
Phase 1 — Foundation
Phase 1 — Foundation | Venue & Logistics | Jun 5 | Distribute Denver RFP | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | Jun 16 | RFP response deadline | Venue | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | Jun 17 | Site visits begin | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | Jun 19 | Venue selection decision | Joint | P2 — High | Not Started
Phase 1 — Foundation | Venue & Logistics | Jun 22 | Venue contract executed | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Speaker Coordination | Jun 25 | Speaker carryover confirmations + Mountain West net-new | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Registration | Jun 26 | Eventbrite listing live | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Travel | Jun 26 | Hotel block secured | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Sponsorship | Jun 30 | Speaker cost-share agreements issued | Gwen | P2 — High | Not Started
Phase 1 — Foundation | Marketing & Outreach | Jul 1 | Mountain West Apollo list built | Gwen | P2 — High | Not Started
Phase 2 — Build
Phase 2 — Build | Speaker Coordination | Jul 4 | Speaker bio + headshot deadline | Speaker | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | Jul 6 | Marketing one-pager + flyer | Gwen | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | Jul 6 | Speaker spotlight social rotation | Gwen | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | Jul 7 | Apollo broker outreach (3A) | Gwen | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | Jul 8 | Speaker call #2 | Joint | P2 — High | Not Started
Phase 2 — Build | Marketing & Outreach | Jul 10 | LinkedIn DM campaign | Gwen | P2 — High | Not Started
Phase 2 — Build | Speaker Coordination | Jul 12 | Slide decks due + Speaker Brief distributed | Speaker + Gwen | P2 — High | Not Started
Phase 3 — Final Prep
Phase 3 — Final Prep | Venue & Logistics | Jul 14 | Venue walkthrough | Gwen + Venue | P2 — High | Not Started
Phase 3 — Final Prep | Marketing & Outreach | Jul 15 | Apollo follow-up (3B) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jul 16 | Print ROS, name cards, signage, journals | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | Jul 16 | Final headcount to venue | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Marketing & Outreach | Jul 19 | Last-call attendee outreach (3C) | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | Jul 19 | Final confirmation to speakers | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Venue & Logistics | Jul 19 | Confirm AV needs from speakers | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jul 20 | Final ROS locked + distributed | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Registration | Jul 22 | Day-before reminder to attendees | Gwen | P2 — High | Not Started
Phase 3 — Final Prep | Speaker Coordination | Jul 22 | Thomas briefing | Joint | P2 — High | Not Started
Phase 3 — Final Prep | Day-Of | Jul 22 | Pack event bag | Gwen | P2 — High | Not Started
Phase 4 — Day-Of
Phase 4 — Day-Of | Day-Of | Jul 23 · AM | Arrive venue — walk room, check signage | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Venue & Logistics | Jul 23 · AM | F&B + AV walkthrough | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Speaker Coordination | Jul 23 · AM | Speaker check-in + sound check | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Registration | Jul 23 | Doors open — registration table | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | Jul 23 | Run summit per ROS | Joint | P2 — High | Not Started
Phase 4 — Day-Of | Sponsorship | Jul 23 · PM | Happy Hour execution | Gwen | P2 — High | Not Started
Phase 4 — Day-Of | Day-Of | Jul 23 · Close | Collect feedback forms | Gwen | P2 — High | Not Started
Phase 5 — Post-Event
Phase 5 — Post-Event | Post-Event | Jul 24 | Email 4A — attendee thank-you + 2027 series tease | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Jul 24 | Email 4B — speaker thank-you | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Marketing & Outreach | Jul 27 | LinkedIn recap post + series wrap-up | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Jul 31 | Internal recap doc complete | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Budget & Contracts | Aug 3 | Cost-share invoices issued | Gwen | P2 — High | Not Started
Phase 5 — Post-Event | Post-Event | Aug 3 | 2026 series-end debrief — what carries to 2027 | Joint | P2 — High | Not Started
RUN OF SHOW
Time | Action | Owner
TBD | Run-of-Show modeled on Hilton Head — finalized after venue contract | Joint
OPEN ITEMS / RISKS
Item | Owner | Due | Priority
Distribute Denver RFP to venue shortlist | Gwen | Jun 5 | P1 — Critical
RFP response deadline | Venue | Jun 16 | P1 — Critical
Venue selection decision | Gwen + Thomas | Jun 19 | P1 — Critical
Venue contract executed | Gwen | Jun 22 | P1 — Critical
Confirm speaker carryovers post-Chicago | Gwen | Jun 25 | P1 — Critical
Eventbrite listing live | Gwen | Jun 26 | P1 — Critical
Hotel block secured | Gwen | Jun 26 | P1 — Critical
Issue speaker cost-share agreements | Gwen | Jun 30 | P1 — Critical
Build Mountain West Apollo list | Gwen | Jul 1 | P2 — High

## Series Dashboard
SERIES DASHBOARD
Cross-event open items · Updated April 27, 2026
ACTIVE OPEN ITEMS — ALL EVENTS
Event | Open Item | Due | Owner | Priority | Status
Dallas (post) | Send Email 4A — Attendee thank-you + Hilton Head invite | 2026-04-27 | Gwen | P1 — Critical | Complete
Dallas (post) | Send Email 4B — Speaker thank-you + Hilton Head ask | Apr 27 | Gwen | P1 — Critical | Complete
Dallas (post) | Send Email 4C — No-show follow-up | Apr 27 | Gwen | P1 — Critical | Complete
Dallas (post) | Final invoices requested (Statler, Encore, Photographer) | 2026-04-28 | Gwen | P1 — Critical | Complete
Dallas (post) | Send Thomas's Chicago invite (Wanza, BJ, Colton, Bryce, Drew, Vicki, Aaron Witner) | Apr 28 | Thomas + Gwen | P1 — Critical | Not Started
Dallas (post) | Distribute Speaker Recap Packet to all 9 speakers | Apr 28 | Gwen | P1 — Critical | Complete
Dallas (post) | Post LinkedIn recap — photos, quotes, Hilton Head CTA | Apr 30 | Gwen | P2 — High | Complete
Dallas (post) | Reconcile final Statler invoice w/ Anastasia | May 5 | Gwen | P2 — High | Complete
Dallas (post) | Issue cost-share invoices to 6 sponsoring companies | Apr 30 | Gwen | P1 — Critical | Not Started
Dallas (post) | Process speaker honorariums (10 business days) | May 7 | Gwen | P2 — High | Not Started
Dallas (post) | Photo gallery — confirm photographer turnaround + send links | May 1 | Gwen | P2 — High | In Progress
Dallas (post) | Internal post-event recap doc — wins, gaps, learnings | Apr 30 | Gwen | P2 — High | Complete
Dallas (post) | Update speaker tracker w/ Hilton Head confirmations as they come in | Rolling | Gwen | P2 — High | In Progress
Hilton Head | Lock Palmetto Dunes contract — room, F&B minimum, AV | May 1 | Gwen + Dom | P1 — Critical | Complete
Hilton Head | Eventbrite listing live — clone Dallas structure | May 1 | Gwen | P1 — Critical | Complete
Hilton Head | Speaker confirmations / Hilton Head cost-share agreements out | May 9 | Gwen | P1 — Critical | Not Started
Hilton Head | Hotel block secured | May 1 | Gwen | P1 — Critical | Complete
Hilton Head | Happy Hour sponsor confirmed | May 8 | Gwen + Thomas | P2 — High | Complete
Hilton Head | Apollo.io Southeast broker list built | May 4 | Gwen | P1 — Critical | Complete
Hilton Head | LinkedIn Save-the-Date posts launched | May 2 | Gwen | P2 — High | Complete
Hilton Head | Marketing one-pager (Lowcountry version) finalized | May 8 | Gwen | P2 — High | Complete
Hilton Head | Logic in the Lowcountry flyer — printed + digital | May 11 | Gwen | P2 — High | Complete
Hilton Head | Contingency: Speaker cancellation backup defined | May 15 | Gwen + Thomas | P2 — High | Not Started
Hilton Head | Contingency: AV-failure plan (journal-only facilitation) | May 15 | Gwen | P3 — Standard | Not Started
Hilton Head | Contingency: Weather plan (Hilton Head matters here) | May 15 | Gwen + Venue | P2 — High | Not Started
Hilton Head | Contingency: Low-attendance pivot (merge tables) | May 15 | Gwen | P3 — Standard | Not Started
Chicago | RFP distributed to venue shortlist | Apr 27 | Gwen | P1 — Critical | Complete
Chicago | RFP responses received from all 6 venues | May 9 | Gwen + Venues | P1 — Critical | Complete
Chicago | Site visits / walkthroughs of finalists | May 12–14 | Gwen | P1 — Critical | Not Started
Chicago | Venue selection decision | May 15 | Gwen + Thomas | P1 — Critical | Not Started
Chicago | Venue contract execution | May 16 | Gwen | P1 — Critical | Not Started
Chicago | Confirm Dallas/HH speaker carryovers for Chicago | May 20 | Gwen | P1 — Critical | Not Started
Chicago | Identify net-new Midwest speakers (if needed) | May 20 | Gwen + Thomas | P2 — High | Not Started
Chicago | Build Eventbrite listing | May 18 | Gwen | P1 — Critical | Not Started
Chicago | Issue speaker cost-share agreements | May 22 | Gwen | P1 — Critical | Not Started
Chicago | Hotel block secured | May 18 | Gwen | P1 — Critical | Not Started
Chicago | Build Midwest Apollo list (IL, WI, IN, MO) | May 22 | Gwen | P2 — High | Not Started
Chicago | Thomas's Chicago invite list activation (Wanza, BJ, Colton, Bryce, Drew, Vicki, Aaron Witner) | Apr 28 | Thomas | P1 — Critical | Not Started
Denver | Distribute Denver RFP to venue shortlist | Jun 5 | Gwen | P1 — Critical | Not Started
Denver | RFP response deadline | Jun 16 | Venue | P1 — Critical | Not Started
Denver | Venue selection decision | Jun 19 | Gwen + Thomas | P1 — Critical | Not Started
Denver | Venue contract executed | Jun 22 | Gwen | P1 — Critical | Not Started
Denver | Confirm speaker carryovers post-Chicago | Jun 25 | Gwen | P1 — Critical | Not Started
Denver | Eventbrite listing live | Jun 26 | Gwen | P1 — Critical | Not Started
Denver | Hotel block secured | Jun 26 | Gwen | P1 — Critical | Not Started
Denver | Issue speaker cost-share agreements | Jun 30 | Gwen | P1 — Critical | Not Started
Denver | Build Mountain West Apollo list | Jul 1 | Gwen | P2 — High | Not Started
OPEN ITEMS BY EVENT (count)
Event | Total Open | Critical (P1)
Dallas (post) | 12 | 6
Hilton Head | 13 | 5
Chicago | 12 | 10
Denver | 9 | 8