## Dallas Planning Checklist
BUCA vs. BLUEBONNETS · DALLAS SUMMIT · APRIL 23, 2026 · PLANNING CHECKLIST BINDER
The Statler, Dallas · Gwen Diede, Event Director · gdiede@zenithriskstrategies.com · 512-787-7922
# | TASK | PHASE | OWNER | DEADLINE | STATUS | ✓ | NOTES
PHASE 1: NOW
1 | Marketing Materials Drafts & Proofs | Phase 1: Now | Gwen | March 31 | Not Started | FALSE | One-pager, event flyer, website assets — needs all bios + headshots first
2 | Campaign Set | Phase 1: Now | Gwen | March 27 | Not Started | FALSE | SocialPilot calendar, LinkedIn campaign, speaker spotlight schedule
3 | Send Save the Dates | Phase 1: Now | Gwen | March 25 | Not Started | FALSE | Email to all known broker/TPA/employer contacts
4 | Eventbrite | Phase 1: Now | Gwen | March 25 | Not Started | FALSE | Build event page, set ticket price/type, publish + share link
5 | Eventbrite Payout Method | Phase 1: Now | Gwen | March 25 | Not Started | FALSE | Connect bank account or payment method in Eventbrite dashboard
6 | Venue and Contracts Signed | Phase 1: Now | Gwen + Thomas | March 28 | In Progress | FALSE | Statler 95% confirmed — negotiate 27% service fee before signing
7 | Speaker Pptx | Phase 1: Now | Gwen | March 28 | In Progress | FALSE | Fix slides 5, 8, 11 — then distribute to all 9 speakers
PHASE 2: BUILD
1 | Send Invitations | Phase 2: Build | Gwen | April 1 | Not Started |  | Formal invites to registered + warm leads; follow up on save the dates
2 | Speaker Meeting 2 Set | Phase 2: Build | Gwen | April 1 | Not Started |  | Schedule second speaker call — topic confirmations, run-of-show review
3 | Marketing Materials Made & Printed | Phase 2: Build | Gwen | April 7 | Not Started |  | One-pager PDF final. Print quantity TBD based on RSVP count.
4 | AV Package | Phase 2: Build | Gwen + Dee | April 10 | Not Started |  | Confirm AV package with Statler ($700 est.) — mics, projector, screen, clickers
5 | Statler Meeting | Phase 2: Build | Gwen + Dee | April 10 | Not Started |  | Final walk-through call with Dee Skinner (469-776-3722 / dee.skinner@hilton.com)
6 | Finalize Room Layout and Design | Phase 2: Build | Gwen + Dee | April 10 | Not Started |  | Confirm table style (round vs. classroom), stage position, registration table
7 | Agenda Made | Phase 2: Build | Gwen | April 10 | Not Started |  | Final printed agenda for attendees — tied to confirmed run-of-show
8 | Photography Booked | Phase 2: Build | Gwen | April 10 | Not Started |  | Book photographer for event day. Budget TBD. Brief on key shots.
PHASE 3: FINAL
1 | Finalize Catering / Menu | Phase 3: Final | Gwen + Dee | April 16 | Not Started |  | Confirm F&B menu, headcount guarantee, dietary accommodations
2 | Check In List | Phase 3: Final | Gwen | April 18 | Not Started |  | Pull from Eventbrite. Print 2 copies. Alphabetical by last name.
3 | Name Tags Made & Printed | Phase 3: Final | Gwen | April 20 | Not Started |  | Include: attendee name, company, city. Speaker tags — different color/style.
4 | Handouts Made and Printed | Phase 3: Final | Gwen | April 20 | Not Started |  | Printed journals/notebooks, agenda, speaker one-pager, any session materials
5 | Final Planning Checklist Binder | Phase 3: Final | Gwen | April 22 | Not Started |  | Compile all docs: ROS, contacts, vendor info, check-in list, speaker briefs
PHASE 4: DAY-OF
1 | Marketing Materials Made & Printed — Day-Of | Phase 4: Day-Of | Gwen | April 23 | Not Started |  | Confirm all printed materials are in event bag before leaving for Statler
TOTAL ITEMS: 21 · COMPLETED: 0 · IN PROGRESS: 2 · NOT STARTED: 19 |  |  |  |  | Update status column as items are completed →
STATUS LEGEND: |  | Not Started | In Progress | Done