INTERNAL RUN-OF-SHOW

Bluebonnet vs. BUCA  ·  April 23, 2026  ·  GWEN ONLY — COMMAND DOC

⚠ This is your day-of command document. Print it. Have it on you at all times. Everything else is secondary.

PRE-EVENT CHECKLIST — APRIL 22 NIGHT

- Event bag packed: name badges, sign-in sheets, printed ROS (×3), speaker name cards, notebooks, pens, feedback forms

- Thomas briefed — 30 min check-in call done

- Statler room confirmed with Anastasia — setup, F&B, A/V

- All 7 speakers confirmed attending — zero question marks

- Happy hour sponsor confirmed — Jarred Pierce / Unity Preferred Network

- Registration link live and tested in Eventbrite

- Final headcount sent to Anastasia for F&B guarantee

- Brett Morris format confirmed — virtual or in-person

MORNING SEQUENCE — APRIL 23

| TIME | ACTION | STATUS |
| --- | --- | --- |
| 7:30 AM | Arrive at Statler. Walk the room. Check signage, table setup, materials. | [ ] |
| 7:45 AM | Check in with Anastasia — confirm F&B timing and A/V setup. | [ ] |
| 8:00 AM | A/V walkthrough with Fermin Martinez (Encore). Test all presenter connections. | [ ] |
| 8:30 AM | Place name badges, notebooks, pens, and feedback forms at each seat. | [ ] |
| 9:00 AM | F&B confirmed and in position. | [ ] |
| 9:15 AM | Speaker check-in opens. Greet each speaker. Confirm they have what they need. | [ ] |
| 9:30 AM | All speakers present. Thomas accounted for. | [ ] |
| 9:45 AM | Sound check with all mics. Confirm A/V is loaded. | [ ] |
| 9:55 AM | Take position at registration table. | [ ] |
| 10:00 AM | Doors open. Welcome attendees. Direct to sign-in. Breakfast in place. | [ ] |
| 10:50 AM | Signal Thomas — 10 minutes to open. | [ ] |

FULL DAY SEQUENCE

| TIME | SESSION | GWEN NOTES |
| --- | --- | --- |
| 11:00 AM | Thomas opens — Cost Containment Framework | 30 min — signal at 28 min |
| 11:30 AM | Courtney DeWitt — Kerix / DPC | 30 min — signal at 28 min |
| 12:00 PM | Lunch — broker dialogue | 30 min — Gwen works the room |
| 12:30 PM | Brett Morris — Samaritan Fund | 30 min — signal at 28 min |
| 1:00 PM | Tim Hyde — Veracity / Pharmacy | 45 min — signal at 43 min |
| 1:45 PM | Break | 15 min — round up speakers |
| 2:00 PM | Dante Panella — PriceMDs / Bundled | 30 min — signal at 28 min |
| 2:30 PM | David Balat — Direct Care Alliance | 30 min — signal at 28 min |
| 3:00 PM | Jarred Pierce — Unity / Network | 30 min — signal at 28 min |
| 3:30 PM | Hot Seat Panel — Thomas moderates | 30 min — Thomas leads |
| 4:00 PM | Happy Hour begins — Gwen circulates | Open through 6:30 PM |
| 6:30 PM | Event close — collect all feedback forms | Gwen |

TIME SIGNALS FOR SPEAKERS

| SIGNAL | MEANING |
| --- | --- |
| 5 fingers held up | 5 minutes remaining in session |
| 2 fingers | 2 minutes remaining |
| 1 finger + eye contact | Wrap now — 30 seconds |
| Throat cut gesture | Over time — hand to Thomas immediately |

EMERGENCY PROTOCOLS

- Speaker no-show: notify Thomas immediately. Have a 15-min filler ready — extended Q&A or open discussion prompt.

- A/V failure: Fermin Martinez — fermin.martinez@encoreglobal.com. Speakers present verbally while tech is resolved.

- Room over capacity: alert Anastasia. Do not turn people away without checking with Thomas.

- Thomas runs long: step to the front of the room, hold up 2 fingers. He knows the signal.

- Attendee complaint or issue: handle quietly off to the side. Never in front of the room.

KEY CONTACTS — DAY-OF

| CONTACT | ROLE | PHONE / EMAIL |
| --- | --- | --- |
| Thomas Wagner | CEO — primary speaker | 512-409-0352 |
| Anastasia Elie | Statler Catering Sales Manager | Anastasia.Elie@Hilton.com · 469.776.3762 |
| Fermin Martinez | Encore A/V Contact | fermin.martinez@encoreglobal.com |
| Jarred Pierce | Speaker + Happy Hour Sponsor | jarred@unitynetwork.health |

Order Before Growth  ·  Discipline Before Scale  ·  Zenith Risk Strategies  ·  Updated April 10, 2026