DALLAS SUMMIT PLANNING TIMELINE  ·  BUCA vs. Bluebonnets  ·  April 23, 2026  ·  Internal Use

PHASE 1 — FOUNDATION  ·  MARCH 20–31

| DATE / TIME | TASK | OWNER |
| --- | --- | --- |
| March 20 | Send post-call recap email to all speakers + deck | Gwen |
| March 20 | Send registration link to Thomas + Jarred for LinkedIn posts | Gwen |
| March 20 | Confirm Dante's company bio received post-call | Gwen |
| March 20 | Reply to Jarred — confirm using bio from last year | Gwen |
| March 21 | Follow up with Thomas re: Drew (client testimonial) | Gwen |
| March 23 | Send initial broker/attendee outreach emails (Sequence 3A) | Gwen |
| March 24 | Confirm Statler room block for speakers — send booking links | Gwen |
| March 25 | Confirm Hilton Head May 29 with venue | Gwen |
| March 25 | Thomas/Chad/David strategy meeting | Gwen |
| March 27 | Chase Thomas — lock Denver July 23 + Chicago date decision | Gwen |
| March 31 | Confirm all headshots + bios received | Gwen |

PHASE 2 — BUILD  ·  APRIL 1–10

| DATE / TIME | TASK | OWNER |
| --- | --- | --- |
| April 1 | Bio + headshot deadline — send reminder March 28, chase stragglers April 1 | Gwen |
| April 1 | All speaker topic areas confirmed | Gwen + Thomas |
| April 3 | Build + distribute marketing one-pager | Gwen |
| April 3 | Launch speaker spotlight social media campaign | Gwen |
| April 5 | Send broker outreach follow-up (Sequence 3B) to non-responders | Gwen |
| April 7 | Confirm client testimonial speaker (Drew or other) — coordinate hotel | Gwen |
| April 8 | Send Eventbrite / registration reminder to all registered attendees | Gwen |
| April 10 | Distribute Speaker Brief + individual run-of-show to all speakers | Gwen |
| April 10 | Confirm Statler venue details — room setup, F&B, A/V walkthrough | Gwen + Dee |

PHASE 3 — FINAL PREP  ·  APRIL 11–22

| DATE / TIME | TASK | OWNER |
| --- | --- | --- |
| April 14 | Last call attendee outreach email (Sequence 3C) | Gwen |
| April 15 | Print run-of-show, speaker name cards, signage | Gwen |
| April 16 | Confirm final headcount with Statler (F&B guarantee) | Gwen + Dee |
| April 18 | Send final confirmation + day-of details to all speakers (Sequence 2D) | Gwen |
| April 18 | All A/V needs confirmed with every speaker | Gwen |
| April 18 | Final run-of-show locked and distributed to Thomas + Dee | Gwen |
| April 20 | Send day-before reminder to all registered attendees | Gwen |
| April 22 | Thomas briefing call or check-in — 30 min | Gwen + Thomas |
| April 22 | Confirm Happy Hour sponsor logistics — Dante Panella / PriceMDs | Gwen |
| April 22 | Pack event bag: name badges, sign-in sheets, printed ROS, notebooks, pens | Gwen |

PHASE 4 — DAY-OF  ·  APRIL 23

| DATE / TIME | TASK | OWNER |
| --- | --- | --- |
| 7:30 AM | Arrive at The Statler — room setup check, signage, materials placement | Gwen |
| 7:45 AM | Check in with Dee — confirm F&B timing and A/V setup | Gwen |
| 8:00 AM | A/V walkthrough with venue tech | Gwen + AV |
| 8:30 AM | Place name badges, notebooks, pens, feedback forms at each seat | Gwen |
| 9:00 AM | F&B confirmed and in place | Gwen + Dee |
| 9:15 AM | Speaker check-in opens | Gwen |
| 9:45 AM | All speakers present and mic'd — sound check | Gwen |
| 10:00 AM | Doors open to attendees — sign-in at registration table | Gwen |
| 10:10 AM | Signal Thomas — 2 minutes to open | Gwen |
| 11:00 AM | Thomas opens — Journal-First opening session begins | Thomas |
| 11:30 AM | Kerix segment (Courtney DeWitt) | Courtney |
| 12:00 PM | Samaritan Fund segment (Brett Morris) | Brett |
| 12:30 PM | Veracity Pharmacy segment (Ashley Jones) | Ashley |
| 1:10 PM | PriceMDs Specialty segment (Dante Panella) | Dante |
| 1:50 PM | Thomas wraps — self-funded plan thesis close | Thomas |
| 2:10 PM | Hot Seat Panel — all speakers on stage, open Q&A | All Speakers |
| 2:30 PM | Lunch — attendee networking | All |
| 3:30 PM | Unity Network segment (Jarred Pierce) | Jarred |
| 4:10 PM | Close — thank attendees, announce Hilton Head | Thomas + Gwen |
| 4:40 PM | Happy Hour begins — Sponsored by Dante Panella / PriceMDs | Dante |
| 6:00 PM | Event close — collect feedback forms | Gwen |

PHASE 5 — POST-EVENT  ·  APRIL 24–30

- April 24 — Send thank-you email to all attendees + session recap (Sequence 4A)

- April 24 — Send thank-you to all speakers + confirm Hilton Head (Sequence 4B)

- April 25 — Send no-show follow-up + Hilton Head invite (Sequence 4C)

- April 25 — Post event recap on LinkedIn — photos, highlight quotes, Hilton Head CTA

- April 28 — Complete internal post-event recap doc (what worked, what to change, final numbers)

- April 28 — Update speaker tracker with post-event notes

- April 30 — Begin Hilton Head speaker outreach if not already started

Zenith Risk Strategies  ·  Gwen Diede  ·  512-787-7922  ·  Order Before Growth · Discipline Before Scale