## Legend & Instructions
LEGEND & INSTRUCTIONS
Status keys · Field guidance · How to use this tracker
STATUS LEGEND
STATUS | COLOR | MEANING
Not Started | Not Started | RFP has not yet been drafted or sent.
Interested | Interested | Verbal interest expressed; RFP in preparation.
RFP Sent | RFP Sent | Formal RFP submitted; awaiting venue response.
Follow Up | Follow Up | Response overdue or contact info missing — chase required.
In Review | In Review | Proposal received; internal review in progress.
Walkthrough Scheduled | Walkthrough Scheduled | Site visit booked.
Walkthrough Complete | Walkthrough Complete | Site visit complete; venue evaluated.
Awarded | Awarded | Venue selected and contract in negotiation.
Declined | Declined | Venue passed or removed from consideration.
Lost | Lost | Venue unavailable or terms unworkable.
PRIORITY LEGEND
High | High | Actively pursuing — top of consideration set.
Medium | Medium | Viable fallback — keep warm.
Low | Low | Backup option — no proactive outreach.
FIELD INSTRUCTIONS
Avail. | Date availability for the event date — True / False / Pending.
Status | Pipeline stage. Updates auto-color the cell.
Priority | High = top finalist track. Medium = warm. Low = backup. Auto-colors.
Resp Due (Internal · 5/1) | Internal target — what we want responses by.
Resp Due (Hard · 5/9) | Hard deadline per RFP. Anything past this is Follow Up.
Proposal Rcvd | Date proposal arrived. Empty = still waiting.
Walkthrough Date | Site visit date once scheduled.
Walkthrough Status | Not Scheduled / Scheduled / Complete / N/A.
Notes | Anything else worth flagging — pricing notes, contact issues, etc.
HOW TO USE
· Click any cell in Status / Priority / Avail / Walkthrough Status — dropdown arrow appears.
· Status and Priority cells auto-color based on selection.
· Three blank rows at bottom of Active Venues for adding new finds.
· Declined venues are kept in a separate section so they don't pollute counts.
· Summary tab pulls live counts from this sheet — no manual updating needed.
· Denver tab is a placeholder shortlist — fill in contacts when RFP launches Jun 5.

## Summary
RFP SUMMARY DASHBOARD
Chicago + Denver Status · Updated April 27, 2026
CHICAGO RFP — STATUS COUNTS
METRIC | COUNT
Total Active Venues | 7
RFP Sent (awaiting response) | 1
In Review (proposal received) | 6
Follow Up Required (overdue) | 0
Walkthrough Scheduled | 0
Walkthroughs Complete | 0
Awarded | 0
High Priority Venues | 5
Medium Priority Venues | 1
Proposals On File | 5
TIMELINE — KEY DATES
RFP Distributed | Apr 27, 2026
Internal Target Response Deadline | May 1, 2026
Hard Response Deadline | May 9, 2026
Site Visits / Walkthroughs | May 12 – 14, 2026
Decision Target | May 15, 2026
Contract Execution Target | May 16, 2026
Event Date | Thursday, June 18, 2026
OPEN ACTION ITEMS
ACTION | OWNER | DUE | PRIORITY | STATUS
Get Maryann Jajou's email at The Blackstone | Gwen | Apr 28 | High | Not Started
Chase contacts at Chicago Athletic Association, Freehand, Ivy Hotel | Gwen | Apr 28 | Medium | Not Started
Chase outstanding proposals (Blackstone, LaSalle, Hotel Zachary, Congress Plaza) | Gwen | May 5 | High | Not Started
Schedule walkthroughs for top 3 finalists | Gwen | May 9 | High | Not Started
Conduct site visits | Gwen | May 12-14 | High | Not Started
Decision call with Thomas | Joint | May 15 | High | Not Started
Execute venue contract | Gwen | May 16 | High | Not Started

## Chicago RFP
ZENITH · CHICAGO VENUE RFP TRACKER
Engineered to Win · June 18, 2026 · Updated April 27, 2026
QUICK REFERENCE
Internal target deadline | May 1, 2026 — work toward this
Hard deadline | May 9, 2026 — RFP cutoff per RFP doc
Site visits | May 12 – 14, 2026 — finalists invited
Decision target | May 15, 2026
Contract execution | May 16, 2026
Event date | Thursday, June 18, 2026
ACTIVE VENUES
Avail. | VENUE NAME | STATUS | PRIORITY | TOTAL ESTIMATE | CONTACT NAME | TITLE | EMAIL | PHONE | RFP SENT | RESP DUE (Internal · 5/1) | RESP DUE (Hard · 5/9) | PROPOSAL RCVD | DECISION DATE | ROOM BLOCK | ROOM RATE | MTG CAPACITY | MEETING ROOM | F&B MIN | AV EST | VIRTUAL VISIT DATE | NOTES
True | The Blackstone | In Review | High | 12500 | Maryann Jajou | Group Sales Manager | maryann.jajou@theblackstonehotel.com | 312.542.3445 | Apr 27 | May 1 | May 9 | 2026-05-30 | May 8 |  |  |  | 3000 | 9500 |  |  | Email pending — Maryann is new contact replacing Gabriella
Pending | The LaSalle Chicago | RFP Sent | High | 0 | Irina Ciubotaru | Senior Sales Manager | irina.ciubotaru@thelasallechicago.com | 872-365-5844 | Apr 27 | May 1 | May 9 |  | May 8 | 10 rooms | [6 empty] | Active contact updated — was Perla
True | Hotel EMC2 | In Review | High | 7350 | Maere K Reeves | Group Sales Manager | maere@hotelemc2.com | 312-915-0000 | Apr 27 | May 1 | May 9 | Apr 27 | May 8 |  |  |  | 500 | $6,500 | 350 |  | Proposal received Apr 27 — full quote in
True | The Warwick | In Review | Medium | 8699 | Beau Buttacavoli | Director of Business Travel | bbuttacavoli@warwickhotels.com | 312-274-6416 | Apr 27 | May 1 | May 9 | Apr 27 | May 8 |  | 199 |  | 2500 | 6000 |  |  | Proposal received — pricing strong
True | Hotel Zachary | In Review | High | 8500 | Abby Wills | Event Sales Manager | awills@hotelzachary.com | 773-302-2328 | Apr 27 | May 1 | May 9 | 2026-04-28 | May 8 |  |  | 42 | 2500 | 6000
True | Congress Plaza Hotel | In Review | Low | 14000 | Rithik Essrani | Sales Coordinator | salescoordinator@congressplazahotel.com | 312.427.3800 ext. 5169 | Apr 27 | May 1 | May 9 |  | May 8 |  |  |  | 4000 | 10000 |  |  | F&B min on the high side — negotiate waive
True | Sheraton Grand Chicago Riverwalk | In Review | High | 4679 | Jennifer Rivest | Sales Manager | Jennifer.Rivest@marriott.com | (847) 384-2745 | Apr 27 | May 1 | May 9 | Apr 28 | May 8 | 10 rooms | 279 | 40 | 1400 | 3000 |  |  | Proposal received Apr 28
0
0
0
DECLINED · REMOVED FROM CONSIDERATION
Avail. | VENUE NAME | STATUS | PRIORITY | CONTACT NAME | TITLE | EMAIL | PHONE | RFP SENT | RESP DUE (Internal · 5/1) | RESP DUE (Hard · 5/9) | PROPOSAL RCVD | DECISION DATE | ROOM BLOCK | ROOM RATE |  | MEETING ROOM | F&B MIN | AV EST | WALKTHROUGH DATE | WALKTHROUGH STATUS | NOTES
False | The Viceroy | Declined | Medium | Anna Ciesielski | Sales and Catering Coordinator | anna.ciesielski@viceroy.com | 312 586 2143 | Apr 27 | May 1 | May 9 | [9 empty] | N/A | Declined — passed
False | The LondonHouse | Declined | — | [16 empty] | N/A | Declined — passed
False | Freehand Hotel | Lost | Low | 0 |  |  |  |  | Apr 27 | May 1 | May 9 |  | May 8 | [7 empty] | Contact info missing — chase Apr 28
False | Ivy Hotel | Lost | Low | 0 |  |  |  |  | Apr 27 | May 1 | May 9 |  | May 8 | [7 empty] | Contact info missing — chase Apr 28

## Denver RFP
DENVER VENUE RFP TRACKER
Mountain West Summit · July 23, 2026 · RFP launches Jun 5
QUICK REFERENCE
RFP Distribution Target | June 5, 2026
Internal Target Response Deadline | June 12, 2026
Hard Response Deadline | June 16, 2026
Site Visits / Walkthroughs | June 17 – 18, 2026
Decision Target | June 19, 2026
Contract Execution Target | June 22, 2026
Event Date | Thursday, July 23, 2026
SHORTLIST · PENDING RFP DISTRIBUTION
Avail. | VENUE NAME | STATUS | PRIORITY | CONTACT NAME | TITLE | EMAIL | PHONE | RFP SENT | RESP DUE (Internal · 5/1) | RESP DUE (Hard · 5/9) | PROPOSAL RCVD | DECISION DATE | ROOM BLOCK | ROOM RATE | MTG CAPACITY | MEETING ROOM | F&B MIN | AV EST | VIRTUAL VISIT DATE | TOTAL ESTIMATE | NOTES
Pending |  | Not Started | High | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | High | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | High | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | Medium | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | Medium | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | Medium | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled
Pending |  | Not Started | Low | [5 empty] | Jun 5 | Jun 12 |  | Jun 19 | [6 empty] | Not Scheduled

## Lists (hidden)
Status | Priority | Availability | Walkthrough
Not Started | High | True | Not Scheduled
Interested | Medium | False | Scheduled
RFP Sent | Low | Pending | Complete
Follow Up |  |  | N/A
In Review
Walkthrough Scheduled
Walkthrough Complete
Awarded
Declined
Lost